## Slide 1: Agentic AI Data Quality & Pipeline Assurance Platform
Implementation Plan & Cost Estimate
September 2026
ADE Test Control Tower — Horizon A/B Roadmap

## Slide 2: Executive summary
Existing ADE Test Control Tower v0.2 already runs real dbt-core and real Airflow — this program evolves it, it does not replace it
Two-horizon plan: a real, working vertical slice first (8 weeks), then the full enterprise target architecture (12 months)
Horizon A proves the “Revenue Quality Certification” scenario end to end: business contract → AI-generated checks → real execution → reconciliation → evidence-grounded RCA → remediation → re-test → certification
Horizon B adds PostgreSQL, Temporal, full agent architecture, 4 warehouse + 3 pipeline adapters, cost/scale/optimization engines, enterprise UI, and multi-cloud deployment portability
Combined program: ≈ $6.0–6.1M over ≈ 14 months, US-based senior team — ROM estimate, ±35%

## Slide 3: A two-horizon delivery strategy
Prove it real and small first. Fund the enterprise build from a working demo, not a deck.

## Slide 4: Horizon A vs. Horizon B
Horizon A — Real vertical slice
  8 weeks
  Extends existing v0.2 code — no rewrite
  Domain model, quality rule engine, evidence + grounding, 5 agents, DuckDB reconciliation
  Client-demonstrable end to end
  ≈ $370K–380K
Horizon B — Full enterprise build
  12 months
  PostgreSQL, Temporal, full agent supervisor, LLM gateway
  4 warehouse + 3 pipeline adapters, cost/scale/optimization engines
  Next.js control tower, SSO, Docker/K8s/multi-cloud
  ≈ $5.6–5.7M

## Slide 5: Horizon A — what gets built (8 weeks)
Domain model: BusinessConcept, QualityContract, QualityRule, Evidence, AgentClaim, Incident, Certification
Adapter abstraction: DataPlatformAdapter/PipelineAdapter ABCs — existing dbt-core, Airflow, dbt Cloud code refactored in, not rewritten
Quality Rule Engine: canonical rule model + SQLGlot compiler (DuckDB dialect) + dbt-test backend
Context Intelligence (slice): structured ContextPackage from business contract + dbt manifest + Airflow metadata
Transformation Intelligence: SQLGlot analysis of SQL → inputs/outputs/CASE/JOIN/FILTER/GROUP BY
5 agents: Context, Transformation, Quality, Evidence, RCA — typed I/O, one LLM gateway
Grounding Gateway: claim/evidence status machine (SUPPORTED / UNVERIFIED / CONFLICTED)
Reconciliation: row count, aggregate, key coverage, hash — source-to-target
Revenue Quality Certification demo scenario, replayable end to end

## Slide 6: Horizon A cost — 8 weeks, US-based senior team
Role | FTE | Hours | Cost
Principal Architect | 0.5 | 173 | $38,925
Senior Backend Engineer × 2 | 2.0 | 692 | $128,020
Senior AI/Agent Engineer | 1.0 | 346 | $67,470
Senior Data Engineer | 1.0 | 346 | $62,280
Frontend Engineer | 0.5 | 173 | $30,275
QA Engineer | 0.5 | 173 | $25,085
Technical PM | 0.25 | 87 | $14,272
Labor total | 5.75 | 1,990 | $366,027
Infra / tooling / LLM API |  |  | $5,000–10,000
Horizon A total |  |  | ≈ $370,000–380,000

## Slide 7: Horizon B — what gets built (12 months)
Full adapter layer: production-grade Snowflake/BigQuery/Redshift/Databricks + MWAA/Composer/Astronomer
Full agent architecture: remaining 6 agents + Agent Supervisor + multi-provider LLM Gateway with cost routing
Quality Execution Planner: Scale, Cost, Change and Optimization Intelligence — cost-gated, warehouse-aware
Hierarchical hash/bucket reconciliation for billion-row tables; incremental certification (no unnecessary rescans)
PostgreSQL + pgvector + S3-compatible object storage + Redis; Temporal replacing asyncio orchestration
Full Next.js/React enterprise Control Tower: Data Products, Pipelines, Quality, Contracts, Lineage, Incidents, Evidence, Agents, Certifications, Cost, Administration
OIDC/SAML SSO, RBAC, secrets abstraction, agent tool allowlists, audit trail
Deployment portability: Docker Compose, Kubernetes (cloud-neutral), Terraform per cloud, OpenTelemetry/Prometheus/Grafana

## Slide 8: Horizon B cost — 12 months, US-based senior team
Role | Avg FTE | Hours | Cost
Principal Architect | 1.0 | 2,076 | $467,100
Senior Backend Engineer | 2.5 | 5,190 | $960,150
Senior AI/Agent Engineer | 1.5 | 3,114 | $607,230
Senior Data Engineer | 2.0 | 4,152 | $747,360
Senior Frontend Engineer | 1.5 | 3,114 | $544,950
DevOps/Platform Engineer | 1.0 | 2,076 | $373,680
QA/Test Engineer | 1.0 | 2,076 | $301,020
Security Engineer (fractional) | 0.4 | 830 | $166,080
Technical PM | 0.75 | 1,557 | $256,905
UX Designer (fractional) | 0.35 | 727 | $112,623
Labor total | ~12.0 | ~24,900 | $4,537,098
Infra / tooling / third-party |  |  | ≈ $500,000
Contingency (12%) |  |  | ≈ $605,000
Horizon B total |  |  | ≈ $5.6–5.7M

## Slide 9
Combined program: ≈ $6.0–6.1M over ≈ 14 months
Horizon A ($375K, 2 months) + Horizon B ($5.6–5.7M, 12 months)

## Slide 10: What moves this number
Team sourcing mix — this uses 100% US-based senior rates; a blended onshore/offshore delivery model typically brings Horizon B labor down 35–50% (≈ $2.3–3.0M)
How many of the 4 warehouse adapters get live credentials vs. contract-tested-only during the build
Whether all 3 deployment targets (Docker/K8s/cloud-VPC) are needed in year one, or Kubernetes/multi-cloud can be deferred post-GA
LLM cost regime — model choice and caching discipline directly affect ongoing AI spend, not just build cost

## Slide 11: Recommended sequencing
Weeks 1–2: Phase 0 audit + finalize Horizon A scope sign-off
Weeks 3–8: Build Horizon A vertical slice; demo Revenue Quality Certification live
Decision gate: use the Horizon A demo to secure funding/commitment for Horizon B before staffing to 12 FTEs
Months 3–14: Horizon B, phased delivery, quarterly re-costing checkpoints against actuals

## Slide 12: Questions?